## Ark1
Lofthus frukt og saft | WEEK 1: PLANNING |  |  |  |  | WEEK 2: DESIGN |  |  |  |  | WEEK 3: BUILD |  |  |  |  | WEEK 4: FINISH/LAUNCH
| Mon 26 Nov | Tue 27 Nov | Wed 28 Nov | Thu 29 Nov | Fri 20 Nov | Mon 3 Dec | Tue 4 Dec | Wed 5 Dec | Thu 6 Dec | Fri 7 Dec | Mon 10 Dec | Tue 11 Dec | Wed 12 Dec | Thu 13 Dec | Fri 14 Dec | Mon 17 Dec | Tue 18 Dec | Wed 19 Dec | Thu 20 Dec | Fri 21 Dec
PROJECT MANAGER | PROJECT MANAGEMENT, CUSTOMER CONTACT, PROPOSAL AND CONTRACT |  |  |  |  | PROJECT MANAGEMENT, CUSTOMER CONTACT |  |  |  |  | PROJECT MANAGEMENT, CUSTOMER CONTACT |  |  |  |  | PROJECT MANAGEMENT, CUSTOMER CONTACT
PROJECT MANAGER CONTENT DEVELOPER | PROJECT START INITIAL MEETING
PROJECT MANAGER CONTENT DEVELOPER DESIGNER | IDENTIFYING GOALS NEEDS ASSESSMENT PROJECT PLANNING
CONTENT DEVELOPER DESIGNER |  | RESEARCH
PROJECT MANAGER CONTENT DEVELOPER DESIGNER |  |  | STRATEGIC PLANNING
CONTENT DEVELOPER |  |  |  | CONTENT PLANNING
CONTENT DEVELOPER DESIGNER DEVELOPER |  |  |  |  | SITE OUTLINE | SITE STRUCTURE
DESIGNER | [7 empty] | MOODBORD, STYLE TILES |  |  | WIREFRAMES
CONTENT DEVELOPER COPYWRITER | [7 empty] | TEXT CONTENT DEVELOPMENT
PHOTOGRAPH | [7 empty] | PHOTOSHOTING (PORTIFOLIO IMAGES) |  |  | PHOTOSHOTING (EMPLOYEE IMAGES)
CONTENT DEVELOPER DESIGNER | [11 empty] | UX/UI PLANNING AND TESTING |  |  |  | UX/UI TESTING
DEVELOPER | [10 empty] | CODING, INTEGRATION AND SITE BUILD
DEVELOPER | [16 empty] | CROSS PLATFORM AND BROWSER TESTING
DEVELOPER | [17 empty] | VALIDATING
CONTEND DEVELOPER DESIGNER DEVELOPER | [18 empty] | REFINEMENT
PROJECT MANAGER CONTEND DEVELOPER DESIGNER DEVELOPER | [19 empty] | LAUNCH